## Sheet1
Date | Time Spent (in hours) | Work Summary
2009-01-14 | 1 | Initial planning session. Outlined basic plans for the first several weeks, dividing tasks. Began laptop setup, including VPN.
2009-01-16 | 2.5 | Transferred and installed Visual Studio 2005, Firefox, MySQL, HeidiSQL, and NUnit for later usage.
2009-01-19 | 3 | Redesigned the team website to be more aesthetically pleasing and small monitor friendly. Added some documentation.
2009-01-21 | 2 | Troubleshot HeidiSQL not working, solved problem (temporarily / for single powerup).
2009-01-23 | 2 | Troubleshot HeidiSQL / MySQL / Visual Studio. Solved permanently.
2009-01-26 | 1.5 | Received newest version of code and began exploring it and preparing to test it.
2009-01-28 | 0.75 | Began code testing.
2009-01-30 | 2.5 | Continued code testing. Passed along preliminary bug findings to Austyn. Status report 1 presented.
2009-02-02 | 2.25 | Further Phase 1 code testing. Passed along further bug findings to Austyn.
2009-02-04 | 0.75 | Continued code testing. Prepared for stakeholder meeting.
2009-02-06 | 1.25 | Continued code testing. Began implementing stakeholder-desired changes, further learning project code structure in the process. (Query sorting)
2009-02-09 | 1.5 | Received working version of DSS Microsoft Access database. Began exploring the layout and architecture.
2009-02-11 | 2.25 | Continued testing code. Presented status report 2.
2009-02-13 | 1.5 | Continued adding stakeholder-desired changes. (Query sorting.)
2009-02-16 | 1.5 | Began coding database conversion program. Learned initial coding idea was faulty. Only seemed to work on initial use.
2009-02-18 | 2.25 | Continued coding database conversion program. Learned initial coding ideas were faulty. Only seemed to work on initial use. Began mapping Access data columns from actual names to their meaningful equivalent.
2009-02-20 | 1 | Continued mapping Access database.
2009-02-22 | 3 | Finished mapping Access database. Began mapping specific names to their MySQL database equivalent.
2009-02-23 | 1.5 | Finished mapping Access to MySQL. Began converting mapping to actual code. Converted to a small 5-element conversion table.
2009-02-25 | 1.5 | Continued coding on database conversion program. Status report 3 presented.
2009-02-27 | 1.5 | Continued coding on database conversion program. Mapped conversion to a 13-element table. Used 10 record sample. Designed a transfer table identical to actual 42-element table intended as final product.
2009-03-02 | 1 | Caught up on work log. Prepared to meet with stakeholders again.
2009-03-04 | 1.75 | Performed some field testing on the databases program. Worked some on the database field conversions.
2009-03-05 | 0.75 | Met with stakeholders to present progress on the project, as well as a sample of what future tabs for equipment and case notes would look like.
2009-03-06 | 2 | Helped Austyn with stakeholder desired changes to the project. Worked some more on database field conversions.
2009-03-13 | 4 | Began implementing the more difficult field conversions, starting with combo boxes.
2009-03-14 | 3 | Worked implementing the hardest conversions, birthdates and phone numbers.
2009-03-15 | 1 | Finished implementing the conversions.
2009-03-16 | 1.5 | Began testing full implementation of conversion code with the 50 record sample. Added some fixes.
2009-03-18 | 2 | Continued testing of conversion program. Implemented some fixes. Tested database program some.
2009-03-20 | 2 | About an hour preparing for mid-term presentation and 45 minutes presenting.
2009-03-23 | 1.75 | Continued testing on both programs. Implemented some conversion fixes.
2009-03-25 | 0 | Missed meeting.
2009-03-27 | 1.75 | Worked with Austyn to explore implementation limitations of the future phases of the project. Performed a bit of code testing.
2009-03-30 | 1.5 | Worked with Austyn on the implementation changes to the query results page. Modified column sizes for when columns are visible.
2009-04-01 | 2 | Worked on further testing of conversion program and database program. Thought to be done with conversion fixes. Prepared and presented Status Report 4.
2009-04-03 | 1 | Austyn had military engagement, and I encounted version conflict issues in my code with him not present for code comparison.
2009-04-06 | 2.5 | Resolved code conflicts with Austyn's help. Reimplemented some of my Query Results changes lost in the resolution. Continued database code testing.
2009-04-08 | 1.5 | Continued testing database code. Tested action sequences with the potential to wipe the current dataset. (Cancelling out of a query results page, etc.)
2009-04-10 | 1 | Continued testing database code.
2009-04-13 | 2 | Obtained entire database. Began mapping further conversions uncovered in obtaining entire DSS database. (2800 records)
2009-04-15 | 1.75 | Continued implementing newly discovered necessary database field conversions. Prepared and presented Status Report 5.
2009-04-17 | 2.5 | Implemented more database conversions. Continued database code testing.
2009-04-20 | 2.5 | Implemented more database conversions. Managed to get through the whole database. Continued database code testing.
2009-04-22 | 3 | Implemented unconvertible field case notes text. Began implementing equipment loan database conversion table.
2009-04-24 | 2 | Finished implementing and testing the conversion code. Continued database code testing.
2009-04-27 | 2 | Implemented report button on conversion program. Began wrapping up tsting of the database code.
2009-04-29 | 2.25 | About an hour preparing for final presentation, 45 minutes presenting the pre-final presentation to Kenny, and 30 minutes completing laptop review and project abstract.
2009-04-30 | 0.75 | Final presentation presented to CS Department.